Amendment of the Grant contract

Instruction and Steps to follow

- Referential document/sections:

- Grant Contract: General Conditions (Annex II), Article 9 – Amendment of the contract

- Types of contract modification

- Significant modification

Where the modification of the Budget or Description of the Action affects:

- Significant changes in the project description (e.g. modification of project activities, results and/or outputs) that do not affect the basic purpose of the Action, and/or

- The financial impact includes:

  - A transfer between main budget headings involving a variation of more than 25% of the amount originally entered in relation to each concerned main heading for eligible costs, or

  - An amendment of the headings for indirect costs, for the contingency reserve, for in-kind contributions or the amounts or rates of simplified cost options, if applicable.

- Minor modification

- Where the amendment to the Budget or Description of the Action does not affect the basic purpose of the Action, and

- The financial impact is limited to a transfer between items within the same main budget heading including cancellation or introduction of an item, or a transfer between main budget headings involving a variation of 25% or less of the amount originally entered in relation to each concerned main heading for eligible costs. Admin order is still needed!

- Steps to follow for modifying the grant contract

  - For requesting a significant modification

    - Prepare a draft-Request for Contract modification

    - If the requested modification affects the project budget, submit new proposed budget with clearly marked affected budget lines and budget headings

    - Consult the draft-Request for Contract modification with the TAT

    - At least thirty days before the date on which the amendment should enter into force, submit the Request for Contract modification to the Contracting Authority (CA).

    - Sign an Addendum to the Contract (in case the CA approves the Request).

    - Apply the modification(s), as agreed with the Addendum.

  - For introducing and reporting about a minor modification

    - 10 days before the date of applying the modification, inform in writing the Contracting Authority about the change(s) that should be introduced, by submitting the notification to the TAT.

    - Wait for the admin order and then apply the modification.

Request/Notification for Grant Contract modification

(Template)

| Contract Ref. No. |  |  |
| --- | --- | --- |
| Title of the project |  |  |
| Coordinator of the Action |  |  |
| Represented by (names and position) |  | (signature of the authorised representative) |
| Date of submission |  |  |
| Submitted by (names and position) |  |  |

| DESCRIPTION AND JUSTIFICATION OF THE MODIFICATION REQUESTED |  |
| --- | --- |
| - Part(s) of the Contract affected by the modification requested/applied (check all applicable) |  |
| Special conditions : | [specify all articles affected] |
| Annex I: Description of the action : | [specify all sections affected] |
| Annex III: Budget of the action : | [specify all budget headings affected] |
| Other: [please, specify] : | [specify all parts affected] |
| - Detailed description of the modification |  |
| [please, add as many rows as needed to describe the modification] |  |
| - Reasons for requesting the modification |  |
| [please, add as many rows as needed to describe the reasons] |  |
| - Expected impact of the modification on the action |  |
| [please, add as many rows as needed to describe the expected impact] |  |
| - Assumptions and risks after the modification is effective |  |
| [please, add as many rows as needed to present the assumptions and risks] |  |

The description of the requested modification shall be short, clear and concrete.

Do not forget your authorised representative to sign the request/notification!

In case of budget changes – add budget template, clearly presenting changes.

For submitting the Request the Beneficiary may use the template presented on the next page.

TAT – Technical Assistance Team

Use the template on the next page